## Sheet1
NovakBrandy
PAP 1
201602
|  | Time Estimate (Hours) | Actual Time Spent (Hours) | Time Difference (Hours) | Rate
Week 1 / Phase 1 |  |  |  |  | 45
| GoToTraining | 1.5 | 1 | 0.5
| A Course for Confidence | 2 | 1.5 | 0.5
| Anchor Points | 2 | 1 | 1
| Development | 4 | 2.5 | 1.5
| Call to Action - Success! | 2 | 1.5 | 0.5
| Time Estimation & Management | 3 | 1.5 | 1.5
| Project & Portfolio | 2 | 2 | 0
| The Burn Up List | 2 | 1 | 1
| Total Hours | 18.5 | 12 | 6.5
| Estimated Cost | 832.5
| Actual Cost | 540
Week 2 / Phase 2
| GoToTraining | 1.5 | 1 | 0.5
| Call to Action - Failure to Success! | 2 | 1.5 | 0.5
| Mission Statement | 2 | 1 | 1
| Self Evaluation: SWOT | 2 | 0.5 | 1.5
| Project & Portfolio | 2 | 2 | 0
| The Burn Up List | 2 | 1 | 1
| Total Hours | 11.5 | 7 | 4.5
| Estimated Cost | 517.5
| Actual Cost | 315
Week 3 / Phase 3
| GoToTraining | 1.5 | 1 | 0.5
| Call to Action - Encouragement! | 2 | 1.5 | 0.5
| Communicating with Visual Tools | 2 | 2 | 0
| Project & Portfolio | 2 | 2 | 0
| The Burn Up List | 2 | 1 | 1
| Total Hours | 9.5 | 7.5 | 2
| Estimated Cost | 427.5
| Actual Cost | 337.5
Week 4 / Phase 4
| GoToTraining | 1.5 | 1 | 0.5
| Call to Action - Growth! | 2 | 1.5 | 0.5
| SWOT Follow-Up | 2 | 0.5 | 1.5
| Being Paid For Your Work | 2 | 1.5 | 0.5
| Month In Review | 2 | 2 | 0
| Total Hours | 9.5 | 6.5 | 3
| Estimated Cost | 427.5
| Actual Cost | 292.5
Total Estimated Cost |  | 2205
Total Actual Cost |  | 1485